## Summary
BankAuction.co - Requirement Matrix vs Spec v1.0 (9 Oct 2026)
Basis: repo main at 6404be2 + live audit of auction.bizsocio.com on 9 Oct 2026 (see 'Live audit 9 Oct' and 'Issues' tabs). 'Not verified' means not confirmed, not missing.
Status | All | P0 Core | P0 Comm | P1 Intel | P1 Partner | P2 Pro | P2 Scale
Done | 17 | 16 | 0 | 1 | 0 | 0 | 0
Partial | 38 | 27 | 6 | 5 | 0 | 0 | 0
Not built | 47 | 19 | 14 | 5 | 5 | 3 | 1
Not verified | 10 | 5 | 0 | 4 | 0 | 0 | 1
Needs decision | 6 | 3 | 2 | 0 | 0 | 0 | 1
Total | 118 | 70 | 22 | 15 | 5 | 3 | 3
Headline reading
- P0 trust & discovery: lifecycle, distinct counts, city parity are done, tested, deployed and live-verified.
- Map is deployed but shows 0 pins in production because coordinates are missing. Clustering, 'search this area', detail-page map not built.
- Search lacks sort, PIN and date filters. Cards lack share/compare/alert and freshness.
- P0 commercial launch is largely not built: no entitlements, no checkout/webhook found, no alert delivery, no analytics, no audit log, no support tickets, no global security headers or rate limits.
- Undated rounds currently count as ACTIVE; the spec says exclude them. Needs your confirmation before I change it.
- CI and Vercel results for PRs #25/#26 were not read by me. Treat 'Tested' as local unit tests only.
- 9 Oct live audit added 15 issues (4 P0). Biggest: city filter shows ~44% of catalogue (Nashik 8 vs 68), map 0 pins, /auctions pages capped at 48.
Root-cause lead on missing cities: location is filled by an existing AI job (pipeline/geo.ts, enrichLocations, runs on the scheduler tick and after imports). ~5,200 rows still empty means the backlog is not draining or those rows were checked and returned no city. Phase 0 must establish which.
Readiness by area (PM view)
Area |  |  | RAG | Reason
Core data correctness (lifecycle, counts) |  |  | Amber | Logic sound; location coverage ~44%; undated rule differs from spec
Search and filters |  |  | Amber | Works; no sort/PIN/date; city filter hides ~56%; /auctions capped
Map discovery |  |  | Red | Deployed but 0 pins; no clustering
Property detail |  |  | Amber | Core fields good; no map/freshness/risk/share; similar-properties wrong
Data sourcing and compliance |  |  | Amber | Guardrails + tests exist; source register/permissions undocumented
Accounts and premium access |  |  | Red | No entitlements; pricing differs from spec
Payments and billing |  |  | Red | Not live (site says so)
Alerts |  |  | Red | Not live
Partners / teams |  |  | Red | Not built
SEO |  |  | Amber | Sitemap/robots/canonicals OK; 930 thin city URLs
Security and privacy |  |  | Amber | Admin/API protected; no security headers/rate limits; borrower-data question
Admin and reporting |  |  | Amber | Pages exist; not audited live; no audit log/tickets
Launch readiness 20 Oct (paid) |  |  | Red | Commercial P0 not built

## Phase plan
Phase | Goal | Main work (see Matrix, filter 'Work phase') | Exit gate - must be true before next phase | Acceptance tests covered | Owner approvals needed first | Depends on | Team roles | Rough effort (working days, ESTIMATE) | Biggest risk | Open rows | Done rows
Phase 0 - Decide & baseline | Remove ambiguity so the team stops guessing | Decide: undated-round rule, canonical city names, state/city/locality rule, MMR list, plan prices+GST, free-tier masking, refund policy, borrower-data policy, map provider, media policy. Read-only baseline: how many published rows have geoCheckedAt empty vs checked-but-no-city; how many have coordinates, dates, category. Read admin Dashboard/Data Engine, CI and Vercel results for PRs #25/#26. Operator runs recon type-check on a machine with Prisma engines. | Written decisions recorded in Owner decisions sheet; baseline numbers recorded; CI/Vercel results read; AI location provider status known | None (unblocks all) | All Phase 0 decisions (owner) | None | Owner + PM + 1 engineer (read-only) | 2-3 | Decisions slip; team builds on assumptions | 4 | 0
Phase 1 - Trust fixes (code only) | Make everything visitors can see honest and consistent. No production data writes. | Pagination + true totals on /auctions/*; Auction Today view; similar-properties by area; 'N more listings mention <city>, not yet location-verified' link on city pages/search; merge city variants (Vasai/Vasai Virar, Aurangabad/Chhatrapati Sambhajinagar); undated rounds separated from active headline; ?keyword= alias; sort options + stable tiebreak; filter chips/clear-all; security headers + rate limits; thin city pages noindex or minimum-count rule; uncategorised/empty property types; investigate 'Pune' prefix; full disclaimer block. | Every public count equals its results total; no page silently truncates; /auctions/* paginate; security headers present; tests added for each fix; each fix its own PR with CI green and preview reviewed | AT-01, AT-03, AT-04, AT-07 (partly AT-02, AT-05, AT-18) | Undated rule + canonical city names (Phase 0) | Phase 0 | 1-2 full-stack engineers + QA | 5-8 | Changing counts surprises stakeholders; explain before deploy | 25 | 0
Phase 2 - Data foundation | Fill the data the product depends on. Needs approval and rollback plan. | Location: drain existing enrichLocations backlog (already scheduled; confirm why ~5,200 rows lack city), re-check rows that were checked but returned no city, review sample, report remaining unassigned. Coordinates: source reliable lat/long from source data or approved geocoder with precision flag; never guess. Category fill. Source register with terms/robots per source. Data-quality dashboard (missing city/coords/dates/prices, undated, end<start, duplicates). Run-state model (partial/no-change/stale). | Unassigned-city share below agreed threshold (suggest <5%); coordinates present for agreed share with precision flag; before/after counts and rollback documented; dashboard live | AT-05, AT-13, parts of AT-06 | Written approval for each production data run + rollback plan; map provider; source permissions | Phase 0 baseline | 1 data engineer + 1 engineer + reviewer | 8-15 (depends on AI provider and data quality) | Bad AI geocodes; mitigation: sample review before bulk write, reversible log | 12 | 2
Phase 3 - Discovery complete | Finish P0 discovery to spec | Map: clustering, search-this-area, loading/error states, split view, detail-page map; filters PIN/date/possession; cards: freshness, uncertainty label, save/share/compare/alert stubs; detail page: last-checked, source links, reserve history provenance, gallery rules, disclaimers; city pages: map/list, pagination; SEO audit; accessibility pass; coverage counters with as-of. | Map shows real pins; map/list parity proven; detail page meets spec 4.7 core; accessibility + SEO checks pass | AT-06, AT-07, AT-15 (part), AT-18, AT-20 (discovery half) | Map provider/budget | Phase 1, Phase 2 (coordinates) | 2 engineers + designer + QA | 12-18 | Map traffic on free OSM tiles; check policy before launch | 18 | 3
Phase 4 - Commercial launch | Take money safely. Do not start without Phase 0 decisions. | Plans/entitlements; sign-in recovery; consent records; checkout with server-side order, signed webhook, idempotency; GST invoices, refunds, credit notes; alert matching + delivery (email first) with dedupe/unsubscribe; analytics with consent; audit log; support tickets and correction path; backups/restore/RPO-RTO; incident process; premium field/document access enforced server-side and tested against direct URL and caching. | Payment sandbox tests pass (single, duplicate, failed, refund, renewal); entitlement cannot be bypassed by URL or cache; alerts only to opted-in users; backup restore tested; owner signs release checklist | AT-08, AT-09, AT-10, AT-11, AT-17, AT-19, AT-20 | Prices, GST wording, refund policy, free-tier masking, gateway account and test keys, alert providers, borrower-data policy, CA review | Phases 0-3 | 2-3 engineers + QA + CA/legal input | 25-40 | Legal/CA sign-off delays; payment edge cases | 23 | 0
Phase 5 - Intelligence | Explain risk honestly and help buyers act | Evidence-linked risk flags (descriptive, no score), reviewer workflow and corrections, compare, branded client report/share links, Auction of the Day, media rights model + gating. | Every shown flag has evidence + review state; unknown never shown as clear; reports include timestamp, source links, missing-data markers | AT-12, AT-15, AT-16 | Risk rubric, legal service boundary, media policy | Phase 3 | 1-2 engineers + reviewer | 15-25 | Legal wording of risk copy | 9 | 1
Phase 6 - Partner growth | Grow through partners | Partner onboarding, codes/links, 30-day attribution, commission engine with clawback, dashboard, statements. | Attribution and payout totals reconcile on test data | AT-14 | One approved commission schedule + tax rules; agreements | Phase 4 | 1-2 engineers | 15-25 | Commission rules unsettled | 5 | 0
Phase 7 - Pro suite & scale | Professional suite and scale | Team seats and pipeline, Private Desk workflows, language waves, new sources one by one with permission gates, load test. | Each wave passes its own coverage/quality/permission gate | AT-13, AT-17 (team parts) | Team and Desk scope, languages, source permissions, load budget | Phase 4-6 | Per wave | Ongoing | Scope creep | 5 | 0
Launch reality check (20 Oct 2026, 11 days away)
- Phases 0 and 1 are realistic before 20 Oct if decisions arrive within 2 days. Phase 2 depends on the AI location provider and approvals.
- Phases 3 and 4 are not realistic by 20 Oct. The spec says no paid subscriptions until payment, entitlement, refund and support paths pass.
- Suggested option (owner decision): launch 20 Oct as a free discovery site with honest copy ('payments and alerts coming'), paid plans after the Phase 4 gate.
- Effort numbers are rough planning estimates for the team to re-estimate, not commitments.
- Rule for every phase: one focused PR per fix, CI green, preview reviewed, owner approval before merge/deploy, production smoke test after.

## Issues
ID | Severity | Area | Finding | Evidence | Impact | Recommended fix | Needs your approval? | Work phase
I-01 | P0 | Search / Location | City filter hides most listings: Nashik shows 8 but keyword search finds 68 (admin 64). City totals on /cities sum to ~4,068 of 9,304 published, so ~56% have no canonical city. | Live: /properties?city=Nashik = 8 (5 active, 3 completed); ?q=nashik = 68; unmatched include Ozar, Sinnar, Eklahare, Deolali, Igatpuri, Malegaon and plain 'Nashik, 4220xx' addresses | Visitors searching a city see a fraction of supply; homepage tiles understate. PR #25 followed your 'canonical city only' decision, which assumed few unassigned rows. | 1) Show 'N more listings mention <city>, not yet location-verified' link on city pages and search (code only, reversible). 2) Approve a geoCity backfill run with review (data change - needs your written approval). 3) Admin bucket report. | Yes (backfill) | Phase 1 (link) + Phase 2 (backfill)
I-02 | P0 | Map | Map shows 0 pins on production. | Live: all-properties, Mumbai, Bangalore, Pune, Chennai map views = 0 pins | Map feature is invisible to users. Property.latitude/longitude essentially empty. | Approve a coordinate-sourcing task from reliable data; do not geocode vaguely. Add clustering + detail map after. | Yes | Phase 2 (coordinates) + Phase 3 (clustering)
I-03 | P0 | Search | /auctions, /auctions/upcoming, /live, /completed capped at 48 with no pager; page 2 repeats page 1; label reads '48 auction(s)'. | Live fetch of /auctions/upcoming?page=2 returned same first listing | Most auctions unreachable via these pages; count misleading. Breaks AT-07. | Add pagination + true total, or redirect these pages to /properties with status filter. | No | Phase 1 - Trust fixes (code only)
I-04 | P1 | Lifecycle | 'Active' = 6,988 of 9,304 (75%). Undated open rounds count as active; spec says exclude. | Code: auctionLifecycle helper; live totals | Headline opportunity numbers may be inflated. | Count undated separately, exclude from headline. | Confirm rule | Phase 1 - Trust fixes (code only) (after Phase 0 rule)
I-05 | P1 | Detail page | 'Similar Properties' ignores location: a Nashik flat lists Bengaluru, Morbi, Surat. | Live detail page text | Looks broken, hurts trust. | Filter by city/state and type. | No | Phase 1 - Trust fixes (code only)
I-06 | P1 | Location data | Duplicate/variant canonical cities (Vasai / Vasai Virar, Aurangabad / Chhatrapati Sambhajinagar); 972 city pages, 930 city URLs in sitemap. | Live /cities, sitemap.xml | Split counts, thin indexable pages. | Merge variants; only index cities above a minimum count. | Confirm names | Phase 1 - Trust fixes (code only)
I-07 | P1 | Commercial | Pricing differs from spec (Rs 2,500/4,000/7,000 vs 1,499/2,699/4,999); Founding, Single, Team, Private Desk plans absent; payments and alerts 'not live'. | Live /pricing | Cannot take subscriptions on 20 Oct as specified. | Owner approves prices, then build checkout/webhook/entitlements. | Yes | Phase 0 - Decide & baseline then Phase 4 - Commercial launch
I-08 | P1 | Privacy | Premium is sold on 'full borrower name & contact details'. | Live /pricing and detail page | Conflicts with spec section 13 data minimisation; legal exposure. | Decide borrower-data policy before launch. | Yes | Phase 0 - Decide & baseline then Phase 1 - Trust fixes (code only)
I-09 | P1 | Security | Only HSTS header present. No CSP, X-Frame-Options, nosniff, Referrer-Policy. No rate limiting on public forms/login found. | Live headers | Standard hardening gap. | Add headers in next.config + rate limits. | No | Phase 1 - Trust fixes (code only)
I-10 | P1 | Detail page | No map, no last-checked/source freshness, no risk flags, no save/share/compare/alert, thin disclaimer. | Live detail page | Misses most of spec 4.7. | Build in order: freshness, map, share/save, disclaimer, then risk. | No | Phase 3 - Discovery complete
I-11 | P1 | Commercial | No analytics, no audit log, no support tickets, no consent records. | Code scan | Cannot measure funnel or run support. | Build before paid launch. | Yes (tool choice) | Phase 4 - Commercial launch
I-12 | P2 | Catalogue | Property-type counts sum to 8,919 vs 9,304 published (385 uncategorised); 'Vehicles' shows 0. | Live /property-types | Category browse incomplete. | Report uncategorised; hide empty category. | No | Phase 1 - Trust fixes (code only)
I-13 | P2 | Search | Param mismatch: ?keyword= is ignored (returns all 9,304); keyword param is ?q=. | Live | Share links or partner links using keyword= silently return everything. | Accept both or reject unknown params visibly. | No | Phase 1 - Trust fixes (code only)
I-14 | P2 | Detail page | Location label shows 'Pune' in front of the lender for a Nashik property (Flat Jail Road). | Live detail header | Possible wrong location label; cause not investigated. | Investigate source of that label. | No | Phase 1 - Trust fixes (code only)
I-15 | P1 | Verification gap | Admin not audited (not logged in in my browser). CI/Vercel results for PRs #25/#26 unread. Sandbox cannot run build or 4 test files. | Process | Admin 64 vs public 68 differs by definition (admin includes drafts/removed) but is unverified. | Give me a read-only admin login or screenshots of Dashboard/Data Engine; read CI. | Yes | Phase 0 - Decide & baseline

## Live audit 9 Oct
Page / check | What was checked | Expected | Observed result
Home / | Loads, city tiles with active counts | 8 tiles with counts | PASS
Home tile vs results | Tile count == /properties?city&status=active | Equal | PASS (8/8, earlier check)
/properties | Total listings | Total shown | PASS - 9,304
/properties?status=active | Active total | Shown | 6,988 (suspect, I-04)
/properties?status=completed | Completed total | Shown | 2,356; active+completed = 9,344 > 9,304 (40 properties in both - allowed)
/properties?city=Nashik | City filter vs real supply | ~68 | FAIL - 8 (I-01)
/properties?q=nashik | Keyword search | Matches | 68 (works)
/properties?keyword=nashik | Alias param | Filtered | FAIL - returns 9,304 (I-13)
/properties?state=Maharashtra | State filter | Filtered | 1,713 (text fallback in use)
/properties?view=map | Pins | Pins for geocoded rows | FAIL - 0 pins (I-02)
/cities | City list | Clean list | 972 cities, variants (I-06)
/city/nashik | City page | Count + list | Loads; shows only canonical matches
/auctions/* | Pagination, true total | Pager | FAIL (I-03)
/auctions/today | Today view | Exists | FAIL - 404 (I-04b)
/property/<slug> | EMD, increment, dates, doc links | Present | PASS (fields present)
/property/<slug> | Map, last-checked, risk, share | Per spec | FAIL
/property/<slug> | Similar properties | Same area | FAIL (I-05)
/pricing | Plans/prices | Spec prices | FAIL - different prices; copy honest about 'not live'
/login /register | Pages load | 200 | PASS (flows not tested - no account creation allowed)
/my-alerts /saved-properties | Pages load | 200 | PASS (load only)
/contact | Form present | Fields | PASS (not submitted)
/robots.txt | Blocks admin/api/login | Yes | PASS
/sitemap.xml | Valid, sensible | Yes | PASS - 10,268 URLs; thin city URLs (I-06)
/api/v1/properties, /banks | Auth required | 401 | PASS
/api/me | No leak when logged out | {user:null} | PASS
/api/cron/health | Protected | 401 | PASS
/admin | Redirects when logged out | Redirect | PASS (admin itself not audited)
Headers | Security headers | CSP, XFO, nosniff | FAIL - only HSTS (I-09)
/property-types | Counts reconcile | Sum = total | FAIL - 8,919 vs 9,304 (I-12)
/banks | Per-bank counts | Shown | Loads; counts not reconciled
Payments / alerts delivery | Working | Per spec | NOT LIVE (stated on site)

## Matrix
Req ID | Spec § | Phase | Requirement | Status | Evidence in code / live | Gap / new work | Tests | Implemented | Tested | Merged | Deployed | Prod smoke-tested | Owner decision | Work phase
LC-01 | 3.2 | P0 Core | One central lifecycle rule for cards, detail, counts, filters, alerts, reports | Done | src/lib/domain/auctionLifecycle.ts (effectiveAuctionStatus, auctionStatusWhere, activeAuctionWhere); homepage, city, search use it | Alerts/reports do not exist yet, so cannot confirm they will reuse it | tests/auctionLifecycle.test.ts, resolveAuctionStatus.test.ts | Yes | Yes (unit, local) | Yes | Yes | Partial (city tiles + counts checked live) |  | Done - keep regression tests
LC-02 | 3.2 | P0 Core | States: Upcoming, Live, Auction Today, Completed, Cancelled, Postponed | Done | Helpers derive these at read time; IST day boundaries | None known | auctionLifecycle.test.ts (boundary cases) | Yes | Yes (unit, local) | Yes | Yes | Not verified | Approve 'Auction Today' rule wording | Done - keep regression tests
LC-03 | 3.2 | P0 Core | Undated/Needs Review state; undated rounds excluded from trusted active headline and reported separately | Not built | Helper treats undated open rounds as never over, so they count as ACTIVE today | Add Undated state, exclude from active headline, add count in admin data-quality view | None | No | No | No | No | No | Confirm: spec wins over current behaviour | Phase 1 - Trust fixes (code only)
LC-04 | 3.2 | P0 Core | Flag end-before-start and partial-date records for review; never auto-repair | Not verified | src/lib/pipeline/completeness.ts exists; not checked against this rule | Check rule coverage + surface in admin | tests/completeness.test.ts (scope not checked) | Not verified | Not verified | Yes | Yes | No |  | Phase 1 - Trust fixes (code only)
LC-05 | 3.2 | P0 Core | Never overwrite source facts to fix status; status derived at read time | Done | Derived in code; raw values kept (fieldProvenance.ts, PropertyChange) | None known | provenance.test.ts | Yes | Yes (unit, local) | Yes | Yes | Not verified |  | Done - keep regression tests
CT-01 | 3.3 | P0 Core | Count distinct properties, not round rows (AT-03) | Done | cityCounts.ts + cities.ts groupBy on property rows; property-level where in publishedWhere | Other counters (admin, stats) not audited | tests/cityCounts.test.ts (13) | Yes | Yes (unit, local) | Yes | Yes | Yes (live tiles = results) |  | Done - keep regression tests
CT-02 | 3.3 | P0 Core | Catalogue total includes round-less published properties; active excludes them (AT-04) | Done | cities.ts 'total' vs active count; activeAuctionWhere requires a round | None known | cityCounts.test.ts | Yes | Yes (unit, local) | Yes | Yes | Partial |  | Done - keep regression tests
CT-03 | 3.3 | P0 Core | Cancelled/Postponed excluded from active and reported separately | Partial | Excluded from active via lifecycle helper | No separate report/count anywhere | auctionLifecycle.test.ts (exclusion only) | Partial | Partial | Yes | Yes | No |  | Phase 1 - Trust fixes (code only)
CT-04 | 3.3 | P0 Core | Homepage city counts use canonical city only; missing city is a separate bucket (AT-05) | Partial | Live: city totals on /cities sum to ~4,068 of 9,304 published, so ~5,236 (56%) have no usable canonical city. Nashik: 8 by city, 68 by keyword | Bucket is invisible to visitors and admin. Needs report + location backfill | cityCounts.test.ts | Yes | Yes (unit, local) | Yes | Yes | FAIL (visitor-visible gap, see I-01) | Approve geoCity backfill | Phase 1 - Trust fixes (code only)
CT-05 | 3.3 | P0 Core | City card count == results total (AT-01) | Done | Both use publishedWhere. Parity holds, but both exclude listings without canonical city, so the parity is on an incomplete set | None | cityCounts.test.ts + live check of all 8 tiles | Yes | Yes (unit + live) | Yes | Yes | Yes (parity) / FAIL (coverage) |  | Done - keep regression tests
DM-01 | 3.1 | P0 Core | Property: coords AND coordinate precision | Partial | Property.latitude/longitude, geoCity/State/Locality, geoCheckedAt | No precision field; production coordinates are effectively empty (live map = 0 pins) | propertyMap.test.ts (validation only) | Partial | Partial | Yes | Yes | Yes - confirmed gap | Approve data task to source coordinates | Phase 2 - Data foundation
DM-02 | 3.1 | P0 Core | Auction round fields (EMD, increment, inspection, possession, notice, type, dates) | Done | Auction model: emd, minimumIncrement, inspection*, possessionStatus, noticeNumber, auctionType, externalAuctionId | Timezone stored implicitly (IST in logic); possession is free text not typed | None specific | Yes | No | Yes | Yes | Not verified |  | Phase 3 - Discovery complete
DM-03 | 3.1 | P0 Core | Institution/source register with terms review, robots state, coverage, last checked | Partial | Bank, Source, FeedSource, SourceRunLog; admin sources/feeds pages; robotsGate | No explicit terms-review / permission record per source | sourceCompliance.test.ts, robotsRules.test.ts | Partial | Partial | Yes | Yes | Not verified | Approve source register | Phase 2 - Data foundation
DM-04 | 3.1 | P0 Core | Evidence/provenance per field with reviewer + correction history | Partial | fieldProvenance.ts, fieldObservations.ts, PropertyChange, mergeLog | No reviewer identity/correction workflow; not shown to users | provenance.test.ts | Partial | Partial | Yes | Yes | No |  | Phase 2 - Data foundation
DM-05 | 3.1 | P1 Intel | Media/document with permission status, review state | Not verified | Media, Document, MediaAsset, SourceMedia models | Permission/rights fields not confirmed | None | Not verified | No | Yes | Yes | No | Media policy decision | Phase 5 - Intelligence
DM-06 | 3.1 | P0 Comm | User/subscription: plan, entitlement dates, provider IDs, invoices, audit | Not built | User and Payment only | No Subscription/Entitlement/Invoice models | None | No | No | No | No | No | Prices + plans | Phase 4 - Commercial launch
DM-07 | 3.1 | P0 Comm | Saved search/alert with channels, frequency, consent, pause, delivery result | Partial | SavedSearch, Alert (type, filters, active) | No channel, frequency, consent, pause or delivery log | None | Partial | No | Yes | Yes | Not verified |  | Phase 4 - Commercial launch
DM-08 | 3.1 | P1 Partner | Partner/referral entities | Not built | Absent | Full schema | None | No | No | No | No | No | Commission rulebook | Phase 6 - Partner growth
DM-09 | 3.1 | P2 Pro | Team/deal entities | Not built | Absent | Full schema | None | No | No | No | No | No | Team/Private Desk scope | Phase 7 - Pro suite & scale
NAV-01 | 4.1 | P0 Core | Main nav incl. Search, Map View, Cities, Banks, Calendar, How it works, Pricing, Partners, Guides, Help, Sign in | Partial | Pages: properties, cities, banks, how-it-works, pricing, blog, contact, login, register | No auction calendar, no partner page; Map is a toggle, not a nav entry | None | Partial | No | Yes | Yes | Not verified |  | Phase 3 - Discovery complete
HP-01 | 4.2 | P0 Core | Hero + search by keyword/location/PIN with filters | Partial | Home page search exists | PIN-code search not present; filter set not checked | None | Partial | No | Yes | Yes | Not verified |  | Phase 3 - Discovery complete
HP-02 | 4.2 | P0 Core | Coverage counters with 'as of' timestamp from defined metrics | Not built | Stat block hidden. Live home shows city tiles with active counts only | Define metrics, show as-of, re-enable | None | No | No | No | No | Confirmed missing |  | Phase 1 - Trust fixes (code only)
HP-03 | 4.2 | P0 Core | Active city tiles = qualifying properties; link to same-count page | Done | page.tsx tiles -> /properties?city=X&status=active | None | cityCounts.test.ts | Yes | Yes | Yes | Yes | Yes |  | Phase 3 - Discovery complete
HP-04 | 4.2 | P1 Intel | Auction of the Day, recent additions, map discovery, guides, video, pricing sections | Partial | Recent/blog/pricing exist | Auction of the Day not found; map section not on home | None | Partial | No | Yes | Yes | Not verified |  | Phase 3 - Discovery complete
HP-05 | 4.2 | P0 Core | No 'verified title' / 'guaranteed' claims | Done | Claims guard test | None known | tests/publicClaims.test.ts | Yes | Yes (unit) | Yes | Yes | Not verified |  | Done - keep regression tests
SR-01 | 4.3 | P0 Core | Filters: keyword, city, state, locality, bank, type, price, status | Done | publishedWhere.ts + PropertyFilterForm | None | cityCounts.test.ts, propertyMap.test.ts (filter parity) | Yes | Yes (unit) | Yes | Yes | Not verified |  | Done - keep regression tests
SR-02 | 4.3 | P0 Core | Filters: PIN code, auction date range, possession type | Not built | Absent | Add filters + schema/index check | None | No | No | No | No | No |  | Phase 3 - Discovery complete
SR-03 | 4.3 | P0 Core | Sort: newest, deadline, price low/high, relevance; deterministic | Not built | Fixed createdAt desc only; no tiebreaker | Add sort + id tiebreak + URL param | None | No | No | No | No | No |  | Phase 1 - Trust fixes (code only)
SR-04 | 4.3 | P0 Core | Shareable URLs; clear-all and active-filter chips | Partial | Filters in URL. Param names: city, state, locality, q (keyword). Note keyword param ?keyword= is ignored (returns all 9,304) | Chips and clear-all not confirmed | None | Partial | No | Yes | Yes | Partial |  | Phase 1 - Trust fixes (code only)
SR-05 | 4.3 | P0 Core | Count, applied filters, pagination, empty state, reset suggestions | Partial | Count + pagination exist | Reset suggestions not confirmed | propertyMap.test.ts (page params) | Partial | Partial | Yes | Yes | Not verified |  | Phase 1 - Trust fixes (code only)
SR-06 | 4.3 | P0 Core | No silent broadening of location/text matching | Partial | City: canonical only. Live proof: Nashik city filter 8 vs keyword 68. State/locality still use text fallback, so the three filters disagree | Make state, city and locality rules consistent; surface unverified matches instead of hiding them | cityCounts.test.ts | Partial | Partial | Yes | Yes | FAIL (I-01) | Decide on state/locality fallback | Phase 1 - Trust fixes (code only)
CD-01 | 4.4 | P0 Core | Card fields: title, location (+uncertainty label), price, date, institution, status, freshness, thumbnail, risk | Partial | PropertyCard shows most via toPropertyCardData | No freshness, no uncertainty label, no risk indicator | None | Partial | No | Yes | Yes | Not verified |  | Phase 3 - Discovery complete
CD-02 | 4.4 | P0 Core | Card actions: save, share, compare, alert (gated) | Partial | Save exists (SavedProperty) | Share/compare/alert missing | None | Partial | No | Yes | Yes | Not verified |  | Phase 3 - Discovery complete
CD-03 | 4.4 | P0 Core | 'Not available in source' labels; placeholder unless media cleared | Not verified | Not checked | Check card + detail | None | Not verified | No | Yes | Yes | No | Media policy | Phase 1 - Trust fixes (code only)
MP-01 | 4.5 | P0 Core | Map/list toggle | Done | ViewToggle.tsx, properties/page.tsx ?view=map | None | propertyMap.test.ts (15) | Yes | Yes (unit, local) | Yes | Yes | Partial (toggle works) |  | Done - keep regression tests
MP-02 | 4.5 | P0 Core | Plot only usable coordinates; no false geocoding | Done | coordinates.ts (India bounds, finite, not 0,0) | None | propertyMap.test.ts | Yes | Yes (unit) | Yes | Yes | Yes (nothing invented) |  | Done - keep regression tests
MP-03 | 4.5 | P0 Core | Pins show real data on production | Not built | Live: 0 pins on all-properties, Mumbai, Bangalore, Pune, Chennai | Coordinates missing in production data | N/A | Yes | Yes (unit) | Yes | Yes | FAIL (0 pins) | Approve coordinate sourcing task | Phase 2 - Data foundation
MP-04 | 4.5 | P0 Core | Pin summary links to detail; pin<->card selection | Done | PropertyMapView.tsx reducer, text-node popups | Never exercised on real pins in production | propertyMap.test.ts (reducer) | Yes | Yes (unit) | Yes | Yes | NOT VERIFIED (no pins) |  | Done - keep regression tests
MP-05 | 4.5 | P0 Core | Clustering at zoomed-out levels (required) | Not built | No cluster library | Add clustering | None | No | No | No | No | No |  | Phase 3 - Discovery complete
MP-06 | 4.5 | P0 Core | Desktop split view; mobile map screen with list toggle | Partial | Map + card list; responsive | True split view not confirmed | None | Partial | No | Yes | Yes | Not verified |  | Phase 3 - Discovery complete
MP-07 | 4.5 | P0 Core | 'Search this area' action | Not built | Absent | Add bounds query | None | No | No | No | No | No |  | Phase 3 - Discovery complete
MP-08 | 4.5 | P0 Core | Loading, no-results, no-coordinate, provider-error states | Partial | No-coordinate message seen live; list empty state | Loading + tile/provider error states not confirmed | None | Partial | No | Yes | Yes | Partial |  | Phase 3 - Discovery complete
MP-09 | 4.5 | P0 Core | Approved provider, costs, attribution | Needs decision | Leaflet + OpenStreetMap tiles, no key | OSM tile policy is not for heavy commercial traffic; needs a decision | None | Yes | n/a | Yes | Yes | n/a | Approve provider/budget | Phase 0 - Decide & baseline
CY-01 | 4.6 | P0 Core | Mumbai city vs MMR as separate views | Needs decision | Only city view exists | MMR list is a draft; do not code until validated | None | No | No | No | No | No | Validate MMR list | Phase 0 - Decide & baseline
CY-02 | 4.6 | P0 Core | City page: active count, catalogue count, labels, filters, pagination | Partial | city/[slug]: active list capped at 48 with 'See all' link. Live /cities lists 972 cities | Page size 48 with 'See all N' link instead of real pagination; no filters | cityCounts.test.ts (counts) | Partial | Partial | Yes | Yes | Partial |  | Phase 1 - Trust fixes (code only)
CY-03 | 4.6 | P0 Core | City page map/list discovery | Not built | Absent on city pages | Reuse map toggle | None | No | No | No | No | No |  | Phase 3 - Discovery complete
CY-04 | 4.6 | P0 Core | Unassigned/unknown location totals reported | Not built | Computed in cities.ts but never displayed. Live gap ~56% of catalogue | Show 'N more listings mention <city>, not yet location-verified' and an admin bucket report | cityCounts.test.ts | Partial | Yes (unit) | Yes | Yes | FAIL | Approve geoCity backfill | Phase 1 - Trust fixes (code only)
CY-05 | 4.6 | P2 Scale | Useful unique SEO city/institution pages, no thin pages | Not verified | City, bank pages exist | Not audited for thin/duplicate content | None | Not verified | No | Yes | Yes | No |  | Phase 3 - Discovery complete
DT-01 | 4.7 | P0 Core | Detail: reserve, dates, EMD, increment, institution, type, possession, inspection | Done | property/[slug]/page.tsx fields | Eligibility/process notes not confirmed | None | Yes | No | Yes | Yes | Not verified |  | Phase 3 - Discovery complete
DT-02 | 4.7 | P1 Intel | Prior rounds with status/date/reserve history; provenance per value | Partial | Prior rounds table (reserve, EMD, dates, status) | No per-value provenance or reserve-history chart | None | Partial | No | Yes | Yes | Not verified |  | Phase 3 - Discovery complete
DT-03 | 4.7 | P0 Core | Source notice link + last-checked timestamp | Not built | Live detail page (flat-jail-road-nashik): no last-checked or source-freshness line | Add last-checked + source link | lastSeen.test.ts (pipeline only) | Not verified | No | Yes | Yes | Confirmed missing |  | Phase 3 - Discovery complete
DT-04 | 4.7 | P0 Core | Detail map when coordinates reliable | Not built | Live detail page has no map | Reuse coordinates.ts + map component | None | No | No | No | No | Confirmed missing |  | Phase 3 - Discovery complete
DT-05 | 4.7 | P1 Intel | Gallery of permitted media with placeholder | Not verified | Media models exist | Rights gating not confirmed | None | Not verified | No | Yes | Yes | No | Media policy | Phase 3 - Discovery complete
DT-06 | 4.7 | P1 Intel | Risk indicators with evidence, confidence, review date | Not built | No risk model or UI | Build per section 5 | None | No | No | No | No | No | Risk rubric | Phase 5 - Intelligence
DT-07 | 4.7 | P1 Intel | Share, compare, alert, client card, request professional help | Partial | Live detail: WhatsApp enquiry + Contact Us only. No save/share/compare/alert/client card | Others absent | None | Partial | No | Yes | Yes | Confirmed | Legal service boundary | Phase 3 - Discovery complete
DT-08 | 4.7 | P0 Core | Research-only disclaimer on detail | Partial | Live detail page has one line 'Always confirm auction details against the official documents'. No full disclaimer block | Detail-page disclaimer not confirmed | publicClaims.test.ts | Partial | Partial | Yes | Yes | Partial |  | Phase 1 - Trust fixes (code only)
CM-01 | 4.8 | P1 Intel | Compare selected properties | Not built | Absent | Build compare UI + URL | None | No | No | No | No | No |  | Phase 5 - Intelligence
CM-02 | 4.8 | P1 Intel | Branded client card/report with timestamp, source links, missing-data flags (AT-15) | Not built | Absent | Build report generator | None | No | No | No | No | No |  | Phase 5 - Intelligence
CM-03 | 4.8 | P1 Intel | Revocable/expiring public share links; private notes separation | Not built | Absent | Share-token model | None | No | No | No | No | No |  | Phase 5 - Intelligence
RK-01 | 5.1 | P1 Intel | Risk fields: possession, litigation, dues, tenancy, title concerns, doc completeness, confidence | Partial | possessionStatus (free text), completeness.ts | Others absent; not evidence-linked | completeness.test.ts | Partial | Partial | Yes | Yes | No | Risk rubric | Phase 5 - Intelligence
RK-02 | 5.2 | P1 Intel | No opaque legal score; descriptive evidence-backed flags | Done | No score exists | Keep it that way until rubric approved | N/A | Yes | n/a | Yes | Yes | n/a | Rubric | Phase 5 - Intelligence
RK-03 | 5.3 | P1 Intel | Reviewer workflow: confirmed/source-stated/uncertain/incorrect/legal review; correction history | Not built | pipeline/review.ts is for duplicates/locations, not risk | Build review states + audit trail | None | No | No | No | No | No |  | Phase 5 - Intelligence
RK-04 | 5.3 | P0 Comm | Public correction/contact path, 24h review SLA (AT-19) | Partial | Contact page + Lead model | No property-linked 'report error', no status/SLA tracking | None | Partial | No | Yes | Yes | Not verified | Staffing SLA | Phase 4 - Commercial launch
SC-01 | 6 | P0 Core | Source register: terms, robots, last success, health, limitations | Partial | Source, FeedSource, SourceRunLog, admin pages | Terms-review record missing | sourceCompliance.test.ts | Partial | Partial | Yes | Yes | Not verified | Approve source register | Phase 2 - Data foundation
SC-02 | 6 | P0 Core | Never bypass robots/401/403/CAPTCHA; stop and record refusal (AT-13) | Done | robotsGate.ts, sourceProtection.ts, httpStatus handling | Not re-audited per source this session | robotsRules.test.ts, httpStatus.test.ts, sourceProtection.test.ts | Yes | Unit tests exist | Yes | Yes | Not verified |  | Phase 2 - Data foundation
SC-03 | 6 | P0 Core | Store source URL, ID, retrieval time, extraction version, field evidence | Partial | externalAuctionId, noticeNumber, fieldProvenance | Extraction version not confirmed | provenance.test.ts | Partial | Partial | Yes | Yes | No |  | Phase 2 - Data foundation
SC-04 | 6 | P0 Core | Conservative dedupe; ambiguous -> review | Done | deduplication/, pipeline/duplicates.ts, admin duplicates page | None known | dedupe.test.ts | Yes | Yes (unit) | Yes | Yes | Not verified |  | Phase 2 - Data foundation
SC-05 | 6 | P0 Core | Run states: success/no-change/blocked/partial/failed/stale distinct | Partial | SourceRunLog status: ok/error/skipped/blocked; schedulerHealth | No partial, no-change or stale state | scheduler.test.ts, zeroYield.test.ts | Partial | Partial | Yes | Yes | Not verified |  | Phase 2 - Data foundation
SC-06 | 6 | P0 Core | Do not ingest findauction.in | Not verified | Not checked in registry this session | Check src/data-sources/registry.ts | sourceClassification.test.ts (scope not checked) | Not verified | No | Yes | Yes | No |  | Phase 2 - Data foundation
SC-07 | 6 | P1 Intel | No media ingest without type + permission | Not verified | Not checked | Audit media pipeline | None | Not verified | No | Yes | Yes | No | Media policy | Phase 2 - Data foundation
AC-01 | 7.1 | P0 Comm | Email/phone sign-in, recovery, preferences | Partial | login/register, userSession.ts, password.ts | No phone/OTP, no recovery flow found | None | Partial | No | Yes | Yes | Not verified |  | Phase 4 - Commercial launch
AC-02 | 7.1 | P0 Comm | Explicit opt-in per channel; simple opt-out; consent log | Not built | Absent | Consent model + UI | None | No | No | No | No | No |  | Phase 4 - Commercial launch
AC-03 | 7.1 | P0 Comm | Saved properties, searches, alert history, invoices, support requests | Partial | saved-properties, my-alerts pages | No invoices, alert history or tickets | None | Partial | No | Yes | Yes | Not verified |  | Phase 4 - Commercial launch
AC-04 | 7.1 | P0 Comm | Server-side authorisation of premium fields/docs/APIs; cache leakage tests (AT-08) | Not built | No tiers or entitlements; public API keys exist (ApiKey) | Entitlement layer + tests | borrowerExposure.test.ts (different issue) | No | No | No | No | No | Free-tier masking decision | Phase 4 - Commercial launch
TR-01 | 7.2 | P0 Comm | Tiers: visitor, free, single notice, quarterly/half/yearly, Founding, Team, Private Desk | Not built | Pricing page only | Plans, entitlements, masking | None | No | No | Yes | Yes | Not verified | Approve plans | Phase 4 - Commercial launch
TR-02 | 7.3 | P0 Comm | Approved prices, GST wording, no contradictory prices | Needs decision | Live /pricing: 3 Month Rs 2,500, 6 Month Rs 4,000, 1 Year Rs 7,000, GST included. Spec proposals: 1,499 / 2,699 / 4,999 plus Founding, Single, Team, Desk | Prices differ from spec; no Founding/Single/Team/Desk plans listed | None | No | No | No | No | Yes (page loads, copy honest: payments not live) | Approve prices + GST wording | Phase 0 - Decide & baseline
PY-01 | 7.4 | P0 Comm | Gateway checkout; server-side order; signed webhook; idempotency (AT-09) | Partial | Live /pricing says 'Online payment isn't live yet - contact us to activate a plan manually'. No webhook route in code | No webhook route or checkout flow found under src/app/api | None | Partial | No | Yes | Yes | Confirmed not live | Gateway account + test keys | Phase 4 - Commercial launch
PY-02 | 7.4 | P0 Comm | Entitlement only after verified payment | Not built | No entitlements | Build with PY-01 | None | No | No | No | No | No |  | Phase 4 - Commercial launch
PY-03 | 7.4 | P0 Comm | Recurring (UPI AutoPay/card) with mandate consent | Needs decision | Absent | Only if approved | None | No | No | No | No | No | Approve or drop | Phase 4 - Commercial launch
PY-04 | 7.4 | P0 Comm | GST invoices, credit notes, numbering | Not built | Absent | CA-approved rules first | None | No | No | No | No | No | CA input | Phase 4 - Commercial launch
PY-05 | 7.4 | P0 Comm | Refund policy shown pre-payment; refund/cancel/renew/expiry flows (AT-10) | Not built | Payment.status has 'refunded' only | Policy + flows | None | No | No | No | No | No | Approve refund policy | Phase 4 - Commercial launch
AL-01 | 8 | P0 Comm | Alerts by city/PIN/bank/budget/type/status | Partial | Alert.filters JSON, my-alerts | PIN absent; matching engine not found | None | Partial | No | Yes | Yes | Not verified |  | Phase 4 - Commercial launch
AL-02 | 8 | P0 Comm | Delivery: email, WhatsApp, push; immediate + digest (AT-11) | Not built | Live /pricing says personalised alerts 'planned and not yet available'. No provider code | Choose providers, templates, jobs | None | No | No | No | No | Confirmed not live | Providers + cost | Phase 4 - Commercial launch
AL-03 | 8 | P0 Comm | Dedupe, new vs material change, delivery log, retry | Not built | Absent | Build | None | No | No | No | No | No |  | Phase 4 - Commercial launch
AL-04 | 8 | P1 Partner | Retention workflows (weekly digest, day-14, day-60, renewal) | Not built | Absent | Build after AL-02 | None | No | No | No | No | No | Consent rules | Phase 6 - Partner growth
PT-01 | 9.1 | P1 Partner | Partner application, agreement, code/link, 30-day attribution | Not built | Absent | Full build | None | No | No | No | No | No | Commission rulebook | Phase 6 - Partner growth
PT-02 | 9.2 | P1 Partner | Commission engine: tiers, clawback, payout statements | Not built | Absent | Full build | None | No | No | No | No | No | One approved schedule + CA | Phase 6 - Partner growth
PT-03 | 9.3 | P1 Partner | Partner dashboard + exports (AT-14) | Not built | Absent | Full build | None | No | No | No | No | No |  | Phase 6 - Partner growth
TM-01 | 9.4 | P2 Pro | Team seats, roles, shared shortlist, pipeline stages, notes, access log | Not built | Absent | Full build | None | No | No | No | No | No | Team scope | Phase 7 - Pro suite & scale
TM-02 | 9.4 | P2 Pro | Firm logo / client card config with safe upload | Not built | Absent | Build with CM-02 | None | No | No | No | No | No |  | Phase 7 - Pro suite & scale
MD-01 | 10 | P1 Intel | Store type, origin, rights, review state per asset; placeholders (AT-16) | Not verified | Live: property type page counts sum to 8,919 vs 9,304 published; 385 uncategorised; 'Vehicles' category shows 0 | Rights fields + public gating not confirmed | None | Not verified | No | Yes | Yes | Partial | Media policy | Phase 5 - Intelligence
MD-02 | 10 | P0 Comm | Document access by entitlement; expiring signed links | Not built | Absent | Depends on AC-04 | None | No | No | No | No | No |  | Phase 4 - Commercial launch
MD-03 | 10 | P1 Intel | Admin content: guides, FAQs, city pages, Auction of the Day, video | Partial | Admin blog, pages, home config | Auction of the Day, video, language variants absent | None | Partial | No | Yes | Yes | Not verified |  | Phase 5 - Intelligence
SE-01 | 11 | P0 Core | Canonical URLs, metadata, sitemap, robots, pagination policy (AT-18) | Partial | Live: robots.txt ok (blocks /admin, /api, /login, /my-alerts); sitemap 10,268 URLs (9,180 property, 930 city); canonical on detail ok; /properties?city=X canonicalises to /properties | 930 city URLs include many tiny cities (thin-page risk, spec 4.6); pagination/indexation policy undocumented | None | Partial | No | Yes | Yes | Partial |  | Phase 1 - Trust fixes (code only)
SE-02 | 11 | P0 Core | No fabricated structured data | Not verified | JsonLd.tsx exists | Audit output fields | None | Not verified | No | Yes | Yes | No |  | Phase 1 - Trust fixes (code only)
LG-01 | 11 | P2 Scale | Hindi + 7 regional languages; labelled translations | Not built | Absent | i18n framework + content | None | No | No | No | No | No | Launch languages | Phase 7 - Pro suite & scale
AN-01 | 11 | P0 Comm | Consent-aware analytics, UTM, signup-to-paid funnel | Not built | No analytics code found | Choose tool, consent banner | None | No | No | No | No | No | Analytics tool | Phase 4 - Commercial launch
AD-01 | 12 | P0 Core | Admin: sources, duplicates, coverage, history, users, leads, payments, media, settings | Partial | Admin pages exist in code; I could not log in to admin in my browser, so admin behaviour was NOT audited live | No risk queue, partner queue, location backlog, support tickets | None | Partial | No | Yes | Yes | NOT VERIFIED |  | Phase 2 - Data foundation
AD-02 | 12 | P0 Core | Data-quality dashboard: missing city/coords/dates/prices, undated, end<start, contradictions | Partial | engine/coverage, completeness.ts, coverage.ts | Undated/end<start/coords not confirmed; unassigned city not shown | coverage.test.ts, completeness.test.ts | Partial | Partial | Yes | Yes | Not verified |  | Phase 2 - Data foundation
AD-03 | 12 | P0 Comm | Operational audit log for admin changes | Not built | No audit-log model found | Add AuditLog + hooks | None | No | No | No | No | No |  | Phase 4 - Commercial launch
AD-04 | 12 | P0 Comm | Support ticket flow with category, SLA, history | Not built | Contact form -> Lead only | Ticket model + admin queue | None | No | No | No | No | No |  | Phase 4 - Commercial launch
AD-05 | 12 | P0 Core | Role-protected, logged, minimised exports; borrower data minimised | Partial | AdminRole, adminAuth; borrower exposure guard | Export logging absent | borrowerExposure.test.ts | Partial | Yes (borrower test) | Yes | Yes | Not verified |  | Phase 1 - Trust fixes (code only)
SEC-01 | 13 | P0 Core | Least privilege, secure sessions, validation | Partial | adminSession/userSession, validation/, httpOnly cookies in admin login | Not security-reviewed | None | Partial | No | Yes | Yes | No |  | Phase 1 - Trust fixes (code only)
SEC-02 | 13 | P0 Core | Rate limits on public endpoints/forms | Not built | Rate handling found only in outbound scrapers | Add limits on login, contact, API | None | No | No | No | No | No |  | Phase 1 - Trust fixes (code only)
SEC-03 | 13 | P0 Core | Secure headers (CSP, HSTS, frame, nosniff) globally | Not built | Live headers on / and detail: only Strict-Transport-Security. No CSP, X-Frame-Options, X-Content-Type-Options, Referrer-Policy | Add headers config | None | No | No | No | No | Confirmed missing |  | Phase 1 - Trust fixes (code only)
SEC-04 | 13 | P0 Comm | Consent/opt-out records; incident, backup, restore, deletion processes | Not built | Not found | Process + tooling | None | No | No | No | No | No |  | Phase 4 - Commercial launch
SEC-05 | 13 | P0 Core | Production changes need PR, CI, preview, owner approval, smoke test | Partial | ci.yml, PR flow followed for #25/#26 | CI/Vercel results for #25/#26 were never read by me | CI | Yes | Not verified | Yes | Yes | Partial |  | Phase 4 - Commercial launch
NF-01 | 14 | P0 Core | Performance: pagination, bounded queries, caching w/o entitlement leakage; CWV targets | Partial | Paginated lists; unstable_cache for city summary | No CWV targets or measurements | None | Partial | No | Yes | Yes | No | Set CWV targets | Phase 1 - Trust fixes (code only)
NF-02 | 14 | P0 Core | Reliability monitoring: errors, import health, webhooks, delivery | Partial | api/cron/health, scheduler watchdog, schedulerHealth.ts | No error tracker, webhook or delivery monitoring | scheduler.test.ts | Partial | Partial | Yes | Yes | Not verified |  | Phase 2 - Data foundation
NF-03 | 14 | P0 Core | Accessibility (keyboard, focus, labels, contrast) | Not verified | Map component has labels; no audit | Run audit | None | Not verified | No | Yes | Yes | No |  | Phase 3 - Discovery complete
NF-04 | 14 | P2 Scale | Load test at 5,000 concurrent users | Needs decision | Absent | Needs budget/environment | None | No | No | No | No | No | Approve scope | Phase 7 - Pro suite & scale
NF-05 | 14 | P0 Core | Backups, restore test, RPO/RTO, rollback | Not built | Not found in repo | Document + test restore | None | No | No | No | No | No | Hosting/DB provider facts | Phase 4 - Commercial launch
AU-01 | 4.3 | P0 Core | /auctions and /auctions/<status> pages paginate and show true totals (AT-07) | Not built | Live: all four pages show '48 auction(s)' and 48 cards; ?page=2 returns the same first listing; no pager links | Add pagination + real total; label is misleading | None | Yes | No | Yes | Yes | FAIL |  | Phase 1 - Trust fixes (code only)
AU-02 | 3.2 | P0 Core | Auction Today has its own view/filter | Not built | Live: /auctions/today returns 'Auctions not found'; tabs show Upcoming/Live/Completed/Postponed/Cancelled only | Add Today view or filter | None | No | No | No | No | FAIL |  | Phase 1 - Trust fixes (code only)
DT-09 | 4.7 | P0 Core | Similar properties are actually similar | Not built | Live: on a Nashik listing, 4 of 8 'Similar Properties' are Bengaluru, Morbi and Surat | Restrict by city/state + type | None | Yes | No | Yes | Yes | FAIL |  | Phase 1 - Trust fixes (code only)
CY-06 | 4.6 | P0 Core | Canonical city list has no duplicate/variant names | Not built | Live /cities: Vasai and Vasai Virar; Aurangabad and Chhatrapati Sambhajinagar; 972 city entries | Merge variants in canonCity; prune tiny cities from index | tests/cityCounts.test.ts (no variant cases) | No | No | No | No | FAIL | Confirm canonical names | Phase 1 - Trust fixes (code only)
PV-01 | 13 | P0 Core | Premium copy matches privacy spec (borrower names) | Needs decision | Live /pricing sells 'full borrower name & contact details'; detail shows 'Borrower details available with Premium' | Spec section 13: minimise borrower personal data; needs documented lawful need | tests/borrowerExposure.test.ts | Yes | Yes | Yes | Yes | Confirmed | Approve borrower-data policy | Phase 0 - Decide & baseline
DQ-01 | 3.2 | P0 Core | Active headline excludes undated rounds | Not built | Live: 6,988 of 9,304 published are 'active' (75%), includes undated open rounds by current rule | True active count unknown until undated rounds are separated | None | No | No | No | No | FAIL (suspect inflation) | Confirm rule change | Phase 1 - Trust fixes (code only)

## Acceptance tests
ID | Test | Status | Evidence | Implemented | Tested | Merged | Deployed | Prod smoke-tested
AT-01 | City count parity | Partial | Parity holds (8/8 tiles) but on canonical-city rows only; ~56% of catalogue has no canonical city | Yes | Yes | Yes | Yes | Yes
AT-02 | Lifecycle | Partial | Active/Live/Today/Completed/Cancelled/Postponed tested; Undated state absent | Yes | Yes | Yes | Yes | NV
AT-03 | Distinct property count | Done | Property-level counts; unit-tested | Yes | Yes | Yes | Yes | Partial
AT-04 | No auction round | Done | Catalogue vs active definitions | Yes | Yes | Yes | Yes | Partial
AT-05 | Unknown city | Partial | Not assigned by fuzzy match (good) but bucket never reported; live gap ~5,236 properties | Yes | Yes | Yes | Yes | FAIL (invisible gap)
AT-06 | Map/list parity | Partial | Filter parity unit-tested; production has no coordinates so pins untested live | Yes | Yes | Yes | Yes | FAIL (0 pins)
AT-07 | Pagination | Partial | /properties paginates; /auctions/* capped at 48 with no pager, page 2 repeats page 1; no sort | Partial | Partial | Yes | Yes | FAIL (/auctions)
AT-08 | Premium access | Not built | No entitlements | No | No | No | No | No
AT-09 | Payment integrity | Not built | No webhook/checkout found | No | No | No | No | No
AT-10 | Renewal/refund | Not built |  | No | No | No | No | No
AT-11 | Alerts | Not built | Alert records only; no delivery | No | No | No | No | No
AT-12 | Risk provenance | Not built | No risk flags | No | No | No | No | No
AT-13 | Source controls | Partial | Robots/HTTP-status tests exist; per-source audit not redone | Yes | Unit tests exist | Yes | Yes | NV
AT-14 | Partner attribution | Not built |  | No | No | No | No | No
AT-15 | Client report | Not built |  | No | No | No | No | No
AT-16 | Media rights | Not verified | Models exist; gating not checked | NV | No | Yes | Yes | No
AT-17 | Privacy/security | Partial | Borrower-data test only | Partial | Partial | Yes | Yes | No
AT-18 | SEO | Partial | Sitemap/robots/canonicals exist; not audited | Partial | No | Yes | Yes | NV
AT-19 | Support and correction | Partial | Contact form only | Partial | No | Yes | Yes | NV
AT-20 | Production smoke test | Partial | Done this session for homepage tiles, search, city, map toggle only. Not done: detail, sign-in, pricing, payment, alerts, admin | Partial | n/a | n/a | Yes | Partial

## Owner decisions
Decision | Spec § | Current state | What it blocks | Needed by
Final plan prices and GST display | 7.3 | Not decided | Blocks checkout, pricing page, partner creatives | Phase 0 - Decide & baseline
Free-tier delay and masking | 7.2 | Not decided | Blocks entitlement layer (AT-08) | Phase 0 - Decide & baseline
Refund policy | 7.4 | Not decided | Blocks refund flow, checkout copy | Phase 0 - Decide & baseline
Map provider | 4.5 | Using free OSM tiles | Confirm acceptable for launch traffic or pick paid provider | Phase 0 - Decide & baseline
Risk rubric | 5.2 | Not decided | Blocks risk flags (P1) | Phase 5 - Intelligence
Source permissions | 6 | Not decided | Blocks any new source | Phase 0 - Decide & baseline
Media permissions | 10 | Not decided | Blocks gallery, thumbnails, AT-16 | Phase 0 - Decide & baseline
Language launch waves | 11 | Not decided | Blocks i18n | Phase 7 - Pro suite & scale
MMR membership list | 4.6 | Draft only | Blocks MMR view | Phase 0 - Decide & baseline
Partner commission schedule | 9.2 | Multiple proposals | Blocks partner build | Phase 6 - Partner growth
Team and Private Desk scope | 9.4 | Not decided | Blocks P2 suite | Phase 7 - Pro suite & scale
Legal service boundary | 4.7 | Not decided | Blocks 'request professional help' | Phase 5 - Intelligence
Borrower names in Premium | 13 | Pricing page sells them | Conflicts with data-minimisation; needs lawful-need policy | Phase 0 - Decide & baseline
Location backfill (geoCity) for ~5,236 unassigned properties | 3.3 | New - from 9 Oct audit | Data change; needs written approval + rollback plan | Phase 0 - Decide & baseline
Load target and budget | 14 | Not decided | Release-gate scope | Phase 7 - Pro suite & scale
Undated rounds: spec rule vs current behaviour | 3.2 | New - from this review | Current code counts undated open rounds as active; spec excludes them | Phase 0 - Decide & baseline
Coordinates for properties | 4.5 | New - from live check | Map has 0 pins; needs owner-approved data task (no invented coordinates) | Phase 0 - Decide & baseline